## Sheet1
Milestone | task names | Fine tune functionality | Date: April 15 |  | Code names | Improve GUI system | Date: April 15
Subcategory #1 |  | Fully functioning milestone system | Date: April 1 |  |  | Get images to cycle with milestone system | Date: April 15
Task1 | Total score display | Add total score and a display for it. This score will be for the mileston system, and will not be used in the shop | Date: March 30 | Person: Jake | Find pictures | Select jpgs. Pick them off the internet. Make sure they are named Damian, or they look like Lampl. | Date: March 30 | Person: Jake
Task2 | Milestone codes | Add custom codes for each milestone. Add short code to act as a save system that will grant the user a certain number of points to spend on whatever they wish. | Date: March 30 | Person: Jake | link pictures | link the cycle of jpgs with the milestones. Have each milestone have a jpg assosiated with it. | Date: April 10 | Person: Grant
Task3 | Milestone entry | Add display and place to enter code. This only can be available right away for use. It should accept a String and needs a button for submitting. | Date: April 1 | Person: Bret | loop pictures | Make it a loop so their will always be an image. The loop only has to go as far as the last milestone. | Date: April 15 | Person: Justin
Subcategory #2 |  | Incorporate store | Date: April 15 |  |  | Make sure the jpg is the button | Date: April 15
Task1 | Adding upgrades | Add more upgrades. Add uprades that have points per seconds. Add a couple upgrades to to the points per click as well. | Date: April 15 | Person: Justin | crop pictures | Crop and edit photos. Make sure they are only heads. | Date: April 1 | Person: Jake
Task2 | add the timer | Add timer so upgrades can be points per second. Add some sort of timer that can run and can keep track of seconds passed to reward the user with the appropraite points. | Date: April 12 | Person: Grant | bound buttons to pictures | Make every image have its own bounds for the button. The jpg = the button. | Date: April 10 | Person: Bret
Task3 | displays for upgrades | Add display for points per click and points per second. This is pretty straitforward. Add a small box for each that displays this information | Date: April 12 | Person:Grant | make jpg react | Try and make the jpg 'react' with each click. I have no clue if we can make it react every time, but it is worth a shot. | Date: April 15 | Person: Bret
Subcategory #3 |  | Add menu | Date: April 10 |  |  | Make it look pretty | Date: April 15
Task1 | add quit option | Add quit button. Basically just add a "Press Q to Quit" | Date: April 1 | Person:Jake | Interior modeling | Make colors pop. Use colors that contrast a little so they pop out and give it a lively look | Date: April 15 | Person: Justin
Task2 | add reset button | Add score reset button. This will be in the menu. Just reset the total score and regular score to 0. | Date: April 10 | Person: Justin | Design layout | Design it in an appealing way. Don’t use weird combonations like purple and orange. | Date: April 10 | Person: Grant
Task3 | add menu | Configure GUI for it. Add a button that expands a menu that has a button for both quitting and reseting score. | Date: April 10 | Person: Bret | texture the background | Add pattern to the background. Add stripes or a cool design to the background of the game, don’t have it just be a flat colored background. | Date: April 15 | Person: Jake